## AUMS
Design and Construct List The following is a list of AUMS documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all AUMS Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
System metering diagrams | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, schematics and single line diagrams. |  |  | x |  |  |  | Yes / No or N/A
Cabling routes | Provide Design Drawings for Cabling routes and co-ordination of data outlets |  |  | x
Confirm room spatial allowances for AUMS equipment | Confirm all equipment installed will fit within the room\riser\ceiling space and maintain accessibility and egress as per Australian Standards |  |  | x |  |  |  | Yes / No or N/A
Detailing of building specific reports & alarms required | Provide documention on project specific reports and alarms that will be reuiqred outputs of the AUMS |  |  | x |  |  |  | Yes / No or N/A
Equipment sizing | Calculations & selections to be provided on the proposed equipment. |  |  |  |  | x
AUMS specification (Where applicable) | Complete an AUMS specification for the project. Include all schedules for points\meters and functional\user requirements |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## BMCS
Design and Construct List The following is a list of BMCS documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all BMCS Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
System metering diagrams | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, schematics and single line diagrams. |  |  | x |  |  |  | Yes / No or N/A
Cabling routes | Provide Design Drawings for Cabling routes and co-ordination of data outlets |  |  | x |  |  |  | Yes / No or N/A
Confirm room spatial allowances for BMCS equipment | Confirm all equipment installed will fit within the room\riser\ceiling space and maintain accessibility and egress as per Australian Standards. |  |  | x |  |  |  | Yes / No or N/A
BMCS specification (Where applicable) | Complete an BMCS specification for the project. Include all schedules for points\meters and functional\user requirements. |  |  | x |  |  |  | Yes / No or N/A
Providing Specific Project Alarms Matrix | Provide Specific Project Alarms Matrix with all user feedback included. |  |  |  |  | x |  | Yes / No or N/A
Providing Controller Points List | Provide documention on project specific BMCS controller points list and third party devices that are connected to the BMCS. |  |  |  |  | x |  | Yes / No or N/A
Provide Network Addressing list | Provide documention on project specific BMCS network adressing. |  |  |  |  | x |  | Yes / No or N/A
Equipment sizing | Calculations & selections to be provided on the proposed equipment. |  |  |  |  | x |  | Yes / No or N/A
Providing specific Controls Functional Description | Provide documention on project specific controls functional description. |  |  | x |  | x |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Electrical
Design and Construct List The following is a list of electrical documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Electrical Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Plan Layouts Drawings (power) | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, schematics and single line diagrams. |  |  | x |  |  |  | Yes / No or N/A
Confirm Room Spatial Allowances with Electrical Equipment | Confirm all equipment installed will fit within the room and maintain accessibility and egress as per AS3000. |  |  | x |  |  |  | Yes / No or N/A
Maximum Demand Calculations | Provide the calculation in editable spreadsheet format, and to satisfy the Supply Authority and to AS/NZS 3000 as a minimum. |  |  | x |  |  |  | Yes / No or N/A
| Note: Equipment data sheets must be provided for all major load groups (i.e. AC Units, chillers, pumps, lifts, comms racks, kitchen equipment etc.). |  |  | x |  |  |  | Yes / No or N/A
Power System Calculations | Provide the calculation using POWERCAD, or approved equal software, covering fault levels, voltage drop, cable sizing and circuit breaker trip unit settings. |  |  |  |  | x |  | Yes / No or N/A
Grading and Discrimination Studies | Provide Grading and Discrimination Studies for review. This must include up to the Substation. |  |  |  |  | x |  | Yes / No or N/A
Power Factor Correction Calculations | Calculations to be provided on the sizing of the PFC unit, the capacitor steps, cable size, future expansion, switchgear and fault rating. |  |  | x |  |  |  | Yes / No or N/A
Application for Connection of newor increased loads to the Supply Authority | Application must be approved prior to design being finalised. |  | x |  |  |  |  | Yes / No or N/A
| Note: Some switchboard upgrades may trigger the requirement for a Service Protective Device or a second egress path as per current AS3000 requirements. | [6 empty] | Yes / No or N/A
Specifications (Where applicable) | Complete an electrical specification for the project. Include all schedules for switchboards, luminaires, cable schedules, spares etc… |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineeer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Fire
Design and Construct List The following is a list of fire documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Fire Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Application for connection to hydraulic services infrastructure for new or increased water supply requirements. | Application to be made to either Sydney Water or University of Sydney (determined by ownership). Application must be approved prior to design being finalised. |  | x |  |  |  |  | Yes / No or N/A
Specifications (Where applicable) | Complete a fire specification for the project. Include schedules for all major items of equipment including FIP, EWIS, pumps, tanks and material types. |  |  | x |  |  |  | Yes / No or N/A
Plan Layout Drawings | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, schematics and single line diagrams. |  |  | x |  | x |  | Yes / No or N/A
Room Spatial Allowances with Fire Equipment | Confirm all equipment proposed will fit within the room/riser/ceiling spaces with sufficient access for maintainance and egress. |  |  | x |  | x |  | Yes / No or N/A
FMS & MNS Connections | Proposed connections, interfacing, system programming, graphic upgrades and network communications between building systems and FMS/MNS to be submitted for approval. |  |  | x |  | x |  | Yes / No or N/A
Water Supply Pressure/Flow Calculations | Provide details of existing water supply pressure/flow requirements via Sydney Water enquiry or by testing the actual supply characteristics and providing results. Water supply graphs (town main + pumped) to be provided to indicate hydrant and fire systems combined water supply design requirements . |  |  | x |  | x |  | Yes / No or N/A
Equipment sizing | Calculations & selections to be provided for all proposed equipment including pumps, tanks, FIP's, MECP's. Future allowances are to be included in these calculations/sizing. |  |  | x |  | x
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements including NCC, Austrailian Standards, Fire Engineering Report, CIS Standards |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineeer. |  |  | x | x | x | x | Yes / No or N/A
Interface Matrix & Block Plans | Interface matrix and block plans proposed to be installed to be submitted for approval prior to installation |  |  |  |  | x |  | Yes / No or N/A
Evacuation Diagrams | Evacuation diagrams proposed to be installed to be submitted for approval prior to installation |  |  |  |  | x |  | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Hydraulics
Design and Construct List The following is a list of hydraulic documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Hydraulic Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Application for connection to hydraulic services infrastructure for new or increased water, gas, sewer and stormwater supply requirements. | Application to be made to either Sydney Water, Local Council or University of Sydney (determined by ownership). Application must be approved by the asset owner prior to design being finalised. |  | x |  |  |  |  | Yes / No or N/A
Specifications (Where applicable) | Complete a hydraulics specification for the project. Include schedules for all major items of equipment including pumps, tanks, hot water plant, water filtration, trade waste equipment, fixtures, fittings and material types. |  |  | x |  |  |  | Yes / No or N/A
Plan Layout Drawings | Design drawings in Autocad (and Revit 3D or GIS model where applicable) format including plans, schematics and detail drawings. |  |  | x |  | x |  | Yes / No or N/A
Room Spatial Allowances for Hydraulic Equipment | Confirm all equipment proposed will fit within the room/riser/ceiling spaces with sufficient access for maintainance and egress. |  |  | x |  | x |  | Yes / No or N/A
BMS & AUMS Connections | Complete a schedule for points and control and functional descriptions for all Hydraulic Services equipment connected to BMS and AUMS. |  |  | x |  | x |  | Yes / No or N/A
Pipework sizing | Calculations to be provided on the sizing of for all hydraulic services pipework, including water, gas, sewer and stormwater. Future allowances are to be included in these calculations/sizing. |  |  | x |  | x |  | Yes / No or N/A
Equipment sizing | Calculations & selections to be provided for all proposed equipment including tanks, pumps, hot water plant, rainwater reuse, stormwater management, meters, trade waste equipment |  |  | x |  | x
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements including NCC, Austrailian Standards, Fire Engineering Report, CIS Standards |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineeer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Lighting
Design and Construct List The following is a list of lighting documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Lighting Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Plan Layouts Drawings (lighting & emergency lighting) | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, lighting control schematics and single line diagrams. |  |  | x |  |  |  | Yes / No or N/A
Confirm Roor Spatial Allowances with Electrical Equipment | Confirm all luminaires installed will fit within the roof and maintain accessibility as per Australian Standards. Luminaire locations should be coordinated with Mechanical Services. |  |  | x |  |  |  | Yes / No or N/A
Lux Level Calculations | Provide calculations using Dialux or AGI for review. |  |  | x |  |  |  | Yes / No or N/A
Lighting Control Methodology | Provide the lighting control methodology for new installations which must follow the Lighting Standard methodology for new areas; provide the type of control being proposed and a lighting control schematic with lighting control network interface (C-BUS or Dynalite) |  |  | x |  |  |  | Yes / No or N/A
Compliance with NCC including Section J, Local Authorities’ regulations and all relevant Australian and New Zealand Standards (AS/NZS). | Provide NCC Section J6 calculations and certifications for energy consumption minimisation. |  |  | x |  |  |  | Yes / No or N/A
| Provide an energy model when the building is over 2000m2. The model should contain details of all equipment so CIS can identify the electricity bill and apportion costs to that building. | [6 empty] | Yes / No or N/A
Specifications (Where applicable) | Complete an electrical specification for the project. Include all schedules for switchboards, luminaires, cable schedules, spares etc… |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineeer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Mechanical
Design and Construct List The following is a list of mechanical documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Mechanical Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Plan Layouts Drawings Duct, Pipe work & equipment location | Design drawings in Autocad (and Revit 3D model where applicable) format including plans, schematics and single line diagrams. |  |  | x |  |  |  | Yes / No or N/A
Confirm Room Spatial Allowances with Mechanical Equipment | Confirm all equipment installed will fit within the room\riser\ceiling space and maintain accessibility and egress as per Australian Standards |  |  | x |  |  |  | Yes / No or N/A
Maximum Demand Calculations | Provide the calculation in editable spreadsheet format, and to satisfy the Supply Authority and to AS/NZS 3000 as a minimum for Mechanical services. |  |  | x |  |  |  | Yes / No or N/A
| Note: Equipment data sheets must be provided for all major load groups (i.e. AC Units, chillers, pumps, etc.). |  |  | x |  |  |  | Yes / No or N/A
Heat Load Calculations | Provide the calculation using Camel, or approved equal software. |  |  |  |  | x |  | Yes / No or N/A
Ductwork & pipe work sizing | Calculations to be provided on the sizing of the duct work & pipe work. Future allowances are to be included in these calculations\sizing. |  |  |  |  | x |  | Yes / No or N/A
Equipment sizing | Calculations & selections to be provided on the proposed equipment. |  |  |  |  | x
Mechanical Specification (Where applicable) | Complete an mechanical specification for the project. Include all schedules for mechanical switchboards, Boilers, chillers,AHU`s,FCU`s,VRV,Fans,Package units,Split systems, etc… |  |  | x |  |  |  | Yes / No or N/A
BMCS Specifications (Where applicable) | Complete an BMCS specification for the project. Include all schedules for points and control\functional description. |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A

## Photo Voltaic
Design and Construct List The following is a list of photovoltaic documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultant/contractor to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Review | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Drawings | Design drawings in Autocad and .pdf format including items identified in Attachment 1: Documentation Checklist |  |  | x | x |  | x | Yes / No or N/A
Confirm Spatial Allowances with Electrical Equipment | Confirm that the selected location for main system components, such as inverters panles etc meet spatial requirements and maintain accessibility |  |  | x |  |  |  | Yes / No or N/A
System sizing calculations | Refer to Attachement 3 of the CIS Solar PV Standard. Sizing must minimise electricity export and maximise system payback |  |  | x |  |  |  | Yes / No or N/A
Specifications | Complete an specification for the system. Include all schedules for switchboards, modules, inverters, mounting equipment and end of life requirements (where applicable) |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Application for Connection of newor increased loads to the Supply Authority | LNSP connection agreement |  |  |  |  | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineer. |  |  | x | x | x | x | Yes / No or N/A
Commissioning records | Submit testing records, photographs. Demonstrate the monitoring system. |  |  |  |  | x |  | Yes / No or N/A
Asset List | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing, monitoring and maintenance | Submit Operaiton and Maintenance Manual. Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed. | [5 empty] | x | Yes / No or N/A

## Vertical Transportation
Design and Construct List The following is a list of vertical transportation documents which CIS require the building service consultant and contractors to provide as part of their package. This is a guide for the consultants/contractors to ensure they meet minimum design components in all projects. These documents will be reviewed by the relevant CIS Services Engineer or their delegate during the design phases. This list does not alleviate the building services consultant’s responsibility to design to the online CIS Design standards.
Design Input - Provided by all Lift Services Consultants on all Projects |  | Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6
Item Required | Detail of the Design Item to be Completed | Initial Project Viability Assessment | Project Brief Preparation and Assessment | Project Endorsement | Project Procurement | Project Delivery | Occupation Management | Compliance Achieved | Building Services Consultant Comments
Plan Layouts Drawings | Design drawings in Autocad (and Revit 3D model where applicable) format including plans and schematics. |  |  | x |  |  |  | Yes / No or N/A
Lift System Performance Calculations | Provide the calculation using Elevate, or approved equal software, covering average Waiting Interval/times and Handling capacity. |  |  | x |  |  |  | Yes / No or N/A
Specifications | Complete a lift specification for the project. Include all schedules for finishes, interiors, fixtures, spares etc… |  |  | x |  |  |  | Yes / No or N/A
Supply of statutory design certifications and certification of compliance to the University standards and other relevant standards. | Complete the design certificate in line with the relevant standards and requirements. |  |  | x | x | x |  | Yes / No or N/A
Safety in Design Documentation | Provide a Safety in Design document for review and approval by the Services Engineeer. |  |  | x | x | x | x | Yes / No or N/A
Asset List (use Asset Labelling Standard) | Proposed final asset list to be submitted for approval |  |  |  |  | x |  | Yes / No or N/A
Inspection, testing and maintenance | Confirm all inspection, testing and preventive maintenance to be perfomed during DLP together with proposed dates when the tasks will be performed | [5 empty] | x | Yes / No or N/A