## Slide 1: Bachelor of Advanced Studies remediation: honours update
Presented by: Hayley Fisher, Nerida Olson, Dan Willis
16 and 17 April 2024
CRICOS 00026A TEQSA PRV12057

## Slide 2: Acknowledgement of country

## Slide 3: Agenda
How will honours application and admission work for BAS students in semester 2 and beyond?
  process
  planned student communications
  contacts for staff and student enquiries
Update on BAS remediation actions and expected timelines.
USER NOTE:
There are more Content Slide options available to add to your presentation by going to:
Home tab > New Slide > Drop down arrow

## Slide 4
Honours
Remediation

## Slide 5: BAS remediation using Arts as an example
Bachelor of Arts and Bachelor of Advanced Studies
(2 x Level 7 degrees)
Complete Honours year via either Bachelor of Arts (Honours) or Bachelor of Advanced Studies (Honours)
[One level 8 award, 1 year]
Complete year 4 to be awarded
Bachelor of Arts and
Bachelor of Advanced Studies
[Two level 7 awards, 4 years]
Can exit with
Bachelor of Arts
[One level 7 award, 3 years]
Options at the end of Year 3*
Does not wish to complete fourth year of study
Wants to complete Advanced Coursework pathway in fourth year
Meets admission requirements for honours and wants to complete honours
*BMus, BEd (Sec) are 4 year degrees, 5 years with BAS
One course of study leading to two awards
Exit BA and BAS; enrol in appended honours degree; awarded
Bachelor of Arts
[One level 7 award, 3 years]
Outcomes at the end of Year 4*

## Slide 6: Student application process
Student receives tailored communications from SFS
Decides they want to apply for honours
Student makes choice: BAS (Honours) OR BX (Honours)
If BAS (Honours) chosen: Application via new process (course page sent from SFS with direct link to app)
If BX (Honours) chosen: Apply via Sydney Courses
Admission process application
Student accepts – exit from combined degree processed and base degree (Bachelor of X) awarded. Student enrols in honours
Student receives offer
Student can seek advice if needed (SAS, SFS, Honours coordinators)
Honours coordinators engaged in decision
Student declines and chooses to continue with BX BAS enrolment -continues with coursework
BAS (Honours) requires completion of two majors
Notes: Honours coordinator: You are still doing what you are always doing- all remains the same.
Students will get tailored communications, they will make the choice at the point of application. Admissions and faculty services will then take care of the assessing and processing.
Honours coordinators will be involved as they always normally are during that process.

## Slide 7: Honours applications for BAS students: key activities
Faculty/School and Undergraduate Studies Committee approval of course resolution changes
Design of honours admissions process for BAS students
BAS (Honours) degree in-system build by Academic Model Team
Build of private course information and admissions pages for application to BAS (Honours) and its streams
Amendments to corporate website, Sydney Courses, current students website to reflect changes
Development of staff intranet page with relevant information
Development of student communications – tailored by segment
 | Activity | Status
1 | Faculty/School and Undergraduate Studies Committee approval of course resolution changes | In progress
2 | Design of honours admissions process for BAS students | Complete
3 | BAS (Honours) degree in-system build by Academic Model Team | In progress
4 | Build of private course information and admissions pages for application to BAS (Honours) and its streams | In progress
5 | Amendments to corporate website, Sydney Courses, current students website to reflect changes | In progress
6 | Development of staff intranet page with relevant information | In progress
7 | Development of tailored student communications | In progress

## Slide 8
Segment | Key Message | 
BAS students – semesters 1 and 2 of year 1 | We hope your first semester is going well Honours choice | Two testamurs Coursework or honours
BAS students – semesters 1 and 2 of year 2, semester 1 of year 3 | We hope your studies are going well Honours choice Two testamurs | Coursework or honours Tips for planning ahead for honours
BAS students – semester 2 of year 3, possibly considering honours S2 | Two testamurs​ Coursework or honours​ | For honours: tailored links to potential options
BAS students – semester 2 of year 3, possibly considering and eligible for honours S2 | Two testamurs​ Coursework or honours​ | For honours: tailored links to potential options and CTA to apply
BAS students enrolled in 4th year Honours​ | Two testamurs​ Choice BX Hons or BAS Hons​ | Future HDR and postgraduate study options Subscription update
BAS students enrolled in 4th year coursework​ | Two testamurs​ Future postgraduate study options | Subscription update
Key dates: Student communications week of 29 April 2024

## Slide 9
Key dates: asset updates
Channel | Date
Intranet: overview of remediation plan and FAQs for staff | 26 April 2024
Representations of BAS courses (offers, websites, publications, information, student facing FAQ’s etc.) ​ | Student and staff mostly completed by 26 April 24 For prospective students, handbook update will be in July

## Slide 10: Student communications – students potentially commencing honours in Semester 2, 2024
Explains options for the final year of degree including:
  Advanced coursework
  Options for honours study, if eligible you can choose:
    to study a Bachelor of X (Honours); or
    to study a Bachelor of Advanced Studies (Honours)
Gives tailored appended honours options for students to choose from in Semester 2, 2024.
Students told they will be awarded two testamurs.
Book an appointment to speak to our specialist staff about best options, including honours path that is best for you.

## Slide 11: Student communications – students earlier in their candidature
Explain options for final year of degree including:
  advanced coursework
  apply for one-year appended honours degree that includes an honours research project
Clarifies that students will receive two testamurs on successful completion of combined BAS degree
Asks student to fill out profile form so they can be sent tailored information

## Slide 12: Contact details for student and staff enquiries
Students will be able to book a consultation. It will be a triage approach whereby SFS, with support from Faculty Services and the Student Centre, would book them in with a relevant specialist
Staff can email: dvc.e-curriculum@sydney.edu.au with any questions
Notes: Include mention that this pack and a link to the process map will be available after the meeting.

## Slide 13
Other remediation activities

## Slide 14: Remediation activities implementation timeline
 | April | May | June | July | August | September | October | November | December
Honours pathway |  |  |  |  |  |  |  |  | 
Two testamurs |  |  |  |  |  |  |  |  | 
New three- year degrees |  |  |  |  |  |  |  |  | 
Underlying causes |  |  |  |  |  |  |  |  | 
new honours application process live
commence communications with BAS graduates
reissue testamurs to BAS graduates
governance, approvals and course build
launch of new degrees
assessment of current state and development of recommendations
embed two testamurs into BAU graduation process for BAS graduands

## Slide 15
Questions?
Help us to create FAQs
What questions do you think students and staff may have that we need to provide answers for?
Please send additional ideas to kate.sanday@sydney.edu.au
Notes: For noting: PDF of the slides and a link to the process map will be available after this briefing.

## Slide 16
Appendix

## Slide 17: BAS remediation plan
BAS remediation plan was endorsed by UE and approved by the VC on 13 March
Two components:
Direct remediation of the BAS degree suite for students, graduates and prospective students
Identification and remediation of underlying multi-factor causes through a series of self-assurance actions

## Slide 18: Remediation of BAS degree suite
Bachelor of X and Bachelor of Advanced Studies: 1 course of study leading to 2 awards and 2 testamurs
Coursework pathway:
  1 x Level 7, Bachelor of X
  1 x Level 7, Bachelor of Advanced Studies
Honours pathway:
  1 x Level 7, Bachelor of X
  1 x Level 8, choice between “Bachelor of X (Honours)” or “Bachelor of Advanced Studies (Honours)”
  The choice of degree name for Honours is only available to currently enrolled students, graduands and graduates. \
  The pathway for honours for any new BAS degree enrolments will be to exit to a “Bachelor of X” and enrol in a “Bachelor of X (Honours)”
Administrative changes to CRICOS register to replace “/” with “and”. As this is an administrative change, no change to course CRICOS codes expected. So, no requirement to change offer letters (and no need to rescind and reissue)
Communications after remediation plan is approved (AB committees at end of March)
  clarification of 2 awards and Honours options
  tailored communication for prospective students across pipeline, Year 4 students and potentially vulnerable groups (including indigenous students, students with disabilities, MySydney scholars, students pending progressions checks)